## Read Me
Test plan template · Quality Engineering Core · chapter 1
Version 1 · free to use. Fill the yellow cells. On every sheet except Read Me and Then and Now, row 5 (grey italic) is an example, not your answer: leave it, then write your own rows below.
How to use it
1. Build your risk sheet in a separate blank sheet first (it is not part of this template).
2. Scope: what is in, what is out, and why. Every 'out' names the risk you accept and its owner.
3. Approach by level: where each kind of check lives, and how deep. Depth follows the risk band (high = every build, medium = every release, low = spot check).
4. Entry-Exit: criteria that anyone could answer yes or no from evidence.
5. Environments, Schedule, Deliverables: fill what your team needs. Keep it short.
6. Then and Now: the sections of the older IEEE 829 test plan and where this template covers them. ISO/IEC/IEEE 29119-3 later replaced IEEE 829, and today many teams keep a living strategy page plus the Definition of Done.
The risk sheet is not part of this template: build it in its own sheet first.

## Scope
Scope
In scope and out of scope, with the reason. Every 'out' item names the risk you accept and who owns it.
In or out | Item | Reason | Accepted risk (for 'out') | Owner (for 'out')
out | Printable care sheets | Few visitors read them | Some visitors read help in English only | Support lead

## Approach by level
Approach by level
Where each kind of check lives, and how deep. Set the depth from the risk band with the formula in column D (high / medium / low in column C). Use one row per level and band if a level holds checks of different bands.
Level | What is checked here | Risk band | Depth (formula) | Run-time budget (s) | Notes
Service (API) | Price rules | high | every build | 60 | Example row
Depth key: high = every build · medium = every release · low = spot check. Bands: level 12-25 high, 6-11 medium, 1-5 low (level = likelihood x impact).

## Entry-Exit
Entry and exit criteria
Write each so that anyone can answer yes or no from evidence.
Type (entry or exit) | Criterion | Evidence that answers it | Who answers
exit | The latest build report shows a result for every planned check | Build report | Test lead

## Environments
Environments and test data
Where the checks run, and what data they need.
Environment | Used for | Data needed | Owner
Staging site | Nightly pipeline run | Test accounts with sample carts | Platform lead

## Schedule
Schedule
Dates and people for this release (a plan, not the strategy).
Activity | Who | Start | End | Depends on
Service checks written | Tester A | Mon | Wed | Test site ready

## Deliverables
Deliverables
What the testing produces.
Deliverable | For whom | When | Where it lives
Risk sheet | Product owner | Week 1 | Team folder

## Then and Now
Then and now
The sections of the older IEEE 829 test plan (first issued 1983), where this template covers them, and what many teams do today. ISO/IEC/IEEE 29119-3 replaced IEEE 829.
IEEE 829 section (then) | Covered by sheet (now) | Today's habit
Features to be tested; features not to be tested | Scope | A short in / out list on the strategy page
Approach | Approach by level | One table: level, depth, budget
Item pass/fail criteria; suspension and resumption criteria | Entry-Exit | Linked to the Definition of Done
Environmental needs | Environments | A line per environment
Schedule; responsibilities; staffing and training needs | Schedule | Held in the team's board
Risks and contingencies | (your risk sheet) | A sorted sheet, reviewed each week
Test deliverables | Deliverables | Links, not documents
Test plan identifier; introduction; test items; testing tasks | (top of your strategy page) | A title and a link to the pipeline
Approvals | Scope (owner column) | A named owner who accepts each excluded risk, in writing